## Product Backlog
ID | Theme | As a/an | I want to… | so that… | Notes | Priority | Sprint # | Status
1 | Simulator | Player | implementing the simulator Architecture | Need to decide technologies, implement project structure & base of the project |  | 1 | 1 | Done
2 | Simulator | Player | implementing the simulator frontend Architecture | implement the base of the frotend |  | 1 | 1 | Done
3 | Simulator | Player | Create a bank account | can deposit & withdraw money |  | 2 | 1 | Done
4 | Simulator | Player | See variation between the prices of shares in the market.so that share prices do not change at the same rate/have the same price. | Can see a variance between the stock price & Can identify a winner easily | use an algorithm to change the price. | 10 | 3 | Done
5 | Simulator | Player | able to buy shares | can make money |  | 5 | 1 | Done
6 | Simulator | Player | need to distribute the game (online play game ) | then everyone can join to the game | Use web technologies | 4 | 1 | Done
7 | Simulator | Broker | Implementing the Broker service - create account | Then players can register to the game through a broker |  | 6 | 2 | Done
8 | Simulator | Broker | Implementing the Broker service - get companies | Then players can see the shares of eah company |  | 7 | 2 | Done
9 | Simulator | Player | Register for the simulator through an user interface (create GUI for player registration) | Easy to player. User friendliness was increased |  | 8 | 2 | Done
10 | Simulator | Player | Sign in to the application through an User interface.(create GUI for sign in) | Easy to player. User friendliness was increased |  | 9 | 2 | Done
11 | Simulator | Broker | implementing the Broker service -get sectors | Player can see what are the available sectors |  | 11 | 3 | Done
12 | Simulator | Broker | implementing the Broker service - buy | Players can buy shares through a brooker |  | 12 | 3 | Done
13 | Simulator | Broker | implementing the Broker service - sell | Players can sell shares through a broker |  | 13 | 3 | Done
14 | Simulator | Player | Create player profile interface | Player will be able to his profile information |  | 14 | 3 | Done
15 | Simulator | Player | Create side bar access in GUI | Player will be able to see navigation links for his profile, portfolio etc. |  | 15 | 3 | Done
16 | Game | Player | Initially we have implement the application as a web page then convert it to game.( create architecture of the game) | Player can see perfect gaming environment |  | 16 | 4 | Done
17 | Game | Player | I need to add multiple players for the game(Create a method to connect players) | Multiple players can connect to the game at the same time |  | 17 | 4 | Done
18 | Game | Player | create a method to get the status of the game | Player will know the status of the game |  | 20 | 4 | Done
19 | Game | Player | As a player I need to know the winner of each game round (Create a method to get winner) | Player will know the winner after the end of each game |  | 18 | 4 | Done
20 | Game | Player | As a player I need to start a new game (Create a method to start a new game) | Player can start a new game |  | 19 | 4 | Done

## Sprint 1
Sprint Goal: | Aiming for a D grade
Start Date: | 2018-05-20
End Date: | 2018-05-28
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
implementing the simulator Architecture | 1 | T1.1 | Reasearch to stock exchange simulator to create architecture | 10 | 10 | Day 1: 5; Day 2: 4; Day 3: 1
|  | T1.2 | Design a solution for stock simulator architecture | 5 | 5 | Day 3: 5
|  | T1.3 | Impkement the solution | 2 | 2 | Day 3: 5
implementing the simulator frontend Architecture | 2 | T2.1 | Research to create frontend architecture | 5 | 5 | Day 3: 3; Day 4: 2
|  | T2.2 | Design a solutio for stock simulator architecture | 2 | 2 | Day 4: 2
|  | T2.3 | Implement the solution | 3 | 3 | Day 4: 3
As a Player, I want to create an bank account | 3 | T3.1 | Reasearch to create bank account | 5 | 5 | Day 5: 4; Day 6: 1
|  | T3.2 | Design a solution for create bank account | 8 | 6 | Day 6: 4; Day 7: 2
|  | T3.3 | Create Test Cases | 3 | 3 | Day 7: 3
|  | T3.4 | Implement the solution | 9 | 9 | Day 7: 6; Day 8: 3
As a Player, I want to be able to buy shares so that I can make money | 4 | T5.1 | Design a Service to handle the incoming request | 3 | 4 | Day 8: 4
|  | T5.2 | Create Test Cases | 1 | 1 | bar: Day 8
|  | T5.3 | Implement the Service | 4 | 3 | Day 8: 3
need to distribute the game (online play game ) | 5 | T6.1 | Research how to use REST / Web services | 6 | 7 | Day 1: 4; Day 2: 3
|  | T6.2 | implement the service | 5 | 5 | Day 3: 5
|  |  | Sprint Countdown: | 71 | 70 | 9 | 7 | 19 | 7 | 4 | 5 | 11 | 11 | 0

## Sprint 1 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop / Stop due to completion | Continue
Implement the simulator architecture |  | Complete the simulator architecture
Implement the frontend architecture |  | Frontend architecture needs further implementations
Create the bank Api |  | May be need to do some changes in future
Create stock market simulator |  | May be need to do some changes in future
Implement service(Buy shares) |  | May be need to do some changes in future
Develop test cases to above mentioned services |  | May be need to do some changes in future
Develop the game as distributed application |  | Complete the task
General Reflections
20% completed from the overall project

## Sprint 2
Sprint Goal: | Aiming for a C grade
Start Date: | 2018-05-29
End Date: | 2018-06-06
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
Implementing the Broker service - create account | 6 | T6.1 | Research to create broker service | 6 | 6 | Day 1: 6
|  | T6.2 | Design a solution for create account | 5 | 5 | Day 1: 2; Day 2: 3
|  | T6.3 | Implement the solution | 5 | 4 | Day 2: 4
|  | T6.4 | implement the test cases | 5 | 5 | Day 2: 5
Implementing the Broker service - get companies | 7 | T7.1 | Research to create get companies | 3 | 3 | Day 2: 3
|  | T7.2 | Design a solution for get companies | 4 | 4 | Day 3: 4
|  | T7.3 | Implement the solution | 6 | 5 | Day 4: 4; Day 5: 1
|  | T7.4 | implement the test cases | 3 | 4 | Day 5: 4
As a payer I need to register for the simulator through an user interface (create GUI for player registration) | 8 | T8.1 | Research how to create GUI | 10 | 10 | Day 5: 5; Day 6: 5
|  | T8.2 | Draw wireframe for the player registration | 1 | 1 | bar: Day 6
|  | T8.3 | Implement the solution | 8 | 7 | Day 6: 4; Day 7: 3
As a player I need to sign in to the application through an User interface.(create GUI for sign in) | 9 | T9.1 | Draw wireframe for the sign in | 1 | 1 | bar: Day 7
|  | T9.2 | Implement the solution | 9 | 9 | Day 8: 5; Day 9: 4
Implement the random trends, market trends to get the variations of the prices | 15 | T15.1 | Read the Project Spec | 4 | 3 | Day 1: 2; Day 3: 1
|  | T15.2 | Design the stock market simulator | 5 | 5 | Day 1: 2; Day 7: 3
|  | T15.3 | Create Test Cases | 1 | 1 | bar: Day 7
|  | T15.4 | Implement the design | 4 | 3 | Day 7: 4
Documentation |  |  | Add details to the documentation | 8 | 8 | Day 8: 4; Day 9: 4
|  |  | Sprint Countdown: | 88 | 84 | 12 | 15 | 5 | 4 | 10 | 10 | 12 | 9 | 8

## Sprint 2 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop / Stop due to completion | Continue
create account to broker service | compelete the task
create get companies to broker | complete the task
implement test cases |  | not competed. Need to transfer to next sprint
Create GUI | some GUI's are completed | May be need to do changes when other components adding
Implement value change algorithm | half of the algorithm is completed | Have to add events and sector trends for the algorithm
Preparing the documents required. |  | Have to add more details in coming sprints
General Reflections
40% completed from the overall project

## Sprint 3
Sprint Goal: | Aiming for a B grade
Start Date: | 2018-06-07
End Date: | 2018-06-15
User Story | PBL ID# | Task ID | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
implementing the Broker service -get sectors | 10 | T10.1 | Research to create get sectors | 3 | 3 | Day 1: 3
|  | T10.2 | Design a solution for create get sectors | 2 | 2 | Day 1: 2
|  | T10.3 | Implement the solution | 4 | 4 | Day 2: 4
|  | T10.4 | implement the test cases | 2 | 3 | Day 3: 3
implementing the Broker service - buy | 11 | T11.1 | Research to create buy shares | 5 | 5 | Day 3: 4; Day 4: 1
|  | T11.2 | Design a solution for buy shares | 6 | 5 | Day 4: 2; Day 5: 3
|  | T11.3 | Implement the solution | 8 | 8 | Day 5: 4; Day 6: 4
|  | T11.4 | implement the test cases | 3 | 3
implementing the Broker service - sell | 12 | T12.1 | Research to create sell shares | 3 | 3 | Day 4: 3
|  | T12.2 | Design a solution for sell shares | 2 | 3 | Day 7: 3
|  | T12.3 | Implement the solution | 5 | 5 | Day 7: 1; Day 8: 4
|  | T12.4 | implement the test cases | 2 | 2 | Day 7: 2
Create player profile interface | 13 | T13.1 | Draw a wireframe | 1 | 1 | bar: Day 8
|  | T13.2 | implement the GUI | 10 | 10 | Day 8: 2; Day 9: 8
Create side bar access in GUI | 14 | T14.1 | Draw a wireframe | 1 | 1 | bar: Day 8
|  | T14.2 | Implement the GUI for the side bar | 10 | 9 | Day 9: 9
As a Player, I want to see variation between the prices of shares in the market.so that share prices do not change at the same rate/have the same price. (sector trends, events & value change) | 15 | T15.5 | Read the Project Spec | 2 | 2 | Day 1: 2
|  | T15.6 | Design the stock market simulator | 6 | 4 | Day 1: 2; Day 7: 2
|  | T15.7 | Create Test Cases | 1 | 1 | bar: Day 7
|  | T15.8 | Implement the design | 7 | 5 | Day 7: 5
|  |  | Sprint Countdown: | 83 | 79 | 9 | 4 | 7 | 6 | 7 | 4 | 14 | 8 | 17

## Sprint 3 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop / Stop due to completion | Continue
Implement the broker service - get sectors | The get sectors implementation completed
Buy the shares through bkoker | The buy method implementation is completed
Sell the shares service implementation | The sell method implementation is completed
Implement player profile info GUI | Player profile info GUI completed
Implementation of side bar access GUI | For the time been it's completed | May be add some another features in next sprint
Add sector trends, events for the value changing algorithm | Value changing algorithm is completed
General Reflections
70% completed from the overall project

## Sprint 4
Sprint Goal: | Aiming for a A grade
Start Date: | 2018-06-16
End Date: | 2018-06-25
User Story | PBL ID# | Task ID | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8
Initially we have implement the application as a web page then convert it to game.( create architecture of the game) | 16 | T16.1 | Research about how to implement game architecture | 6 | 6 | Day 1: 6 | Day 9
|  | T16.2 | Design a solution to create game architecture | 5 | 5 | Day 1: 5
|  | T16.3 | Implement the solution | 8 | 8 | Day 2: 8
|  | T16.4 | Design the test cases | 3 | 3 | Day 1: 3
I need to add multiple players for the game(Create a method to connect players) | 17 | T17.1 | Research about how to implement a method to connect players | 6 | 6 | Day 2: 6
|  | T17.2 | Design a solution to create a method for connect players | 5 | 5 | Day 2: 5
|  | T17.3 | Implement the soution | 8 | 7 | Day 3: 7
|  | T17.4 | Design test cases | 2 | 2 | Day 2: 2
create a method to get the status of the game | 18 | T18.1 | Research about how to implement a method to get the status of the game | 6 | 6 | Day 3: 6
|  | T18.2 | Design a solution to gte the status of the game | 5 | 5 | Day 4: 5
|  | T18.3 | Implementation the solution | 4 | 3 | Day 5: 3
|  | T18.4 | Design the test cases | 2 | 2 | Day 4: 2
As a player I need to know the winner of each game round (Create a method to get winner) | 19 | T19.1 | Research about how to implement a method to get the winner | 4 | 3 | Day 5: 3
|  | T19.2 | Design a solution to get the winner | 3 | 3 | Day 5: 3
|  | T19.3 | Implement a method to get the winner | 3 | 3 | Day 6: 3
|  | T19.4 | Design the test cases | 2 | 2 | Day 5: 2
As a player I need to start a new game (Create a method to start a new game) | 20 | T20.1 | Research about how to implement a method to start a new game | 6 | 4 | Day 7: 4
|  | T20.2 | designa solution | 3 | 3 | Day 8: 3
|  | T20.3 | Implement the solution | 2 | 2
|  | T20.4 | Design test cases | 2 | 2 | Day 8: 2 | 2
Documentation |  |  | Add details to the documentation | 12 | 12 | Day 7: 4; Day 8: 4
|  |  | Sprint Countdown: | 97 | 92 | 14 | 21 | 13 | 7 | 11 | 3 | 8 | 9 | 4
6

## Sprint 4 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop / Stop due to completion | Continue
Create the architecture of the game | Successfully convert the web like appication to the game
Create a method to connect players | Successfully finished. For the time can connect 5 players for each game
Create a method to get the status of the game | can get the status of the game as play or stop & the method implementation us successful
Get the winner of the game | The method to find winner implementation is finish & it's successful
Method for start a new game | The method is implement successfully.
General Reflections
100% completed from the overall project