## Product Backlog
ID | Theme | As a/an | I want to… | so that… | Notes | Priority | Sprint # | Status
| Simulator |  | implementing the simulator Architecture |  |  |  | 1 | Done
| Simulator |  | implementing the simulator Frontend Architecture |  |  |  | 1 | Done
| Simulator | Market | Creating Stock Market (Pre defining data) |  |  |  | 1 | TODO
| Game | Player | show stock data (Pre defined data) |  |  |  | 1 | Done
| Game | Player | Player can buy shares |  |  |  | 1 | Done
| Simulator | Player | Play a game made up of fixed-duration turns | I have only a limited time to decide what to buy and sell | This is an essential property of the game. |  |  | TODO
| Simulator | Player | Know how many turns have passed since the start of the game | I know how far into the game I am |  |  |  | TODO
| Simulator | Player | Have a fixed number of turns in a game | The game has a fixed duration. | We don’t want the game to go on forever… |  |  | TODO
| Simulator | Player | See variation between the prices of shares in the market. | Share prices do not always change at the same rate/have the same price. | This is the stock value model |  | 1 | TODO
| Game | Player | be able to buy shares | they can make money | This needs refinement |  | 1 | TODO
| Game | Player | be able to see the current price of shares | they can decide what to buy/sell |  |  | 1
| Bank | player | I have to create a bank account | to buy shares need money |  |  |  | TODO
| Bank | player | be able to do transaction | to deposit & withdraw money in each turn, also to check balance |  |  |  | TODO
| Player | Broker | Create stock account | Can consist portfolio & transaction history |  |  | 1 | Done

## Sprint 1
Sprint Goal: | Aiming for a D grade
Start Date: | 2016-05-20
End Date: | 2016-05-26
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
implementing the simulator Architecture | 1 | T1.1 | Reasearch to stock exchange simulator to create architecture | 10 | 10
|  | T1.2 | Design a solution for stock simulator architecture | 5 | 5
|  | T1.3 | Impkement the solution | 2 | 2
implementing the simulator frontend Architecture | 2 | T2.1 | Research to create frontend architecture | 5 | 5
|  | T2.2 | Design a solutio for stock simulator architecture | 2 | 2
|  | T2.3 | Implement the solution | 3 | 3
As a Player, I want to create an bank account | 3 | T3.1 | Reasearch to create bank account | 5 | 5
|  | T3.2 | Design a solution for create bank account | 8 | 6
|  | T3.3 | Create Test Cases | 3 | 3
|  | T3.4 | Implement the solution | 9 | 9
As a Player, I want to see variation between the prices of shares in the market.so that share prices do not change at the same rate/have the same price. | 4 | T4.1 | Read the Project Spec | 2 | 2
|  | T4.2 | Design the stock market simulator | 6 | 4
|  | T4.3 | Create Test Cases | 1 | 1
|  | T4.4 | Implement the design | 7 | 5
As a Player, I want to be able to buy shares so that I can make money | 5 | T5.1 | Design a Service to handle the incoming request | 3 | 4
|  | T5.2 | Create Test Cases | 1 | 1
|  | T5.3 | Implement the Service | 4 | 3
need to distribute the game (online play game ) | 6 | T6.1 | Research how to use REST / Web services | 6 | 7
|  | T6.2 | implement the service | 5 | 5
Sprint Countdown:
|  |  |  | 87 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 1 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
Implement the simulator architecture | Complete the simulator architecture
Implement the frontend architecture |  | Frontend architecture needs further implementations
Create the bank Api |  | May be need to do some changes in future
Create stock market simulator |  | May be need to do some changes in future
Implement service(Buy shares) |  | May be need to do some changes in future
Develop test cases to above mentioned services |  | May be need to do some changes in future
Develop the game as distributed application | Complete the task
General Reflections
20% completed from the overall project

## Sprint 2
Sprint Goal: | Aiming for a C grade
Start Date: | 2016-05-20
End Date: | 2016-05-26
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
implementing the Broker service - create account | 7 | T7.1 | Research to create broker service | 6 | 6
|  | T7.2 | Design a solution for create account | 5 | 5
|  | T7.3 | Implement the solution | 5 | 4
|  | T7.4 | implement the test cases | 5 | 5
implementing the Broker service - get companies | 8 | T8.1 | Research to create get companies | 3 | 3
|  | T8.2 | Design a solution for get companies | 4 | 4
|  | T8.3 | Implement the solution | 6 | 5
|  | T8.4 | implement the test cases | 3 | 4
create GUI for player registration | 9 | T9.1 | Research how to create GUI | 10 | 10
|  | T9.2 | Draw wireframe for the player registration | 1 | 1
|  | T9.3 | Implement the solution | 8 | 7
create GUI for sign in | 10 | T10.1 | Draw wireframe for the sign in | 1 | 1
|  | T10.2 | Implement the solution | 9 | 9
documentation | 11 | T11.1 | Add details to the documentation | 8 | 8
|  |  |  | 74 | 72 | 0 | 0 | 0 | 0 | 0
Sprint Countdown:

## Sprint 2 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
create account to broker service | compelete the task
create get companies to broker | complete the task
implement test cases |  | not competed. Need to transfer to next sprint
Create GUI | some GUI's are completed | May be need to do changes when other components adding
General Reflections
40% completed from the overall project

## Sprint 3
Sprint Goal: | Aiming for a B grade
Sprint Goal: | Aiming for a B grade
Start Date: | 2016-05-20
End Date: | 2016-05-26
User Story | PBL ID# | Task ID | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
implementing the Broker service -get sectors | 12 | T12.1 | Research to create get sectors | 3 | 3
|  | T12.2 | Design a solution for create get sectors | 2 | 2
|  | T12.3 | Implement the solution | 4 | 4
|  | T12.4 | implement the test cases | 2 | 3
implementing the Broker service - buy | 13 | T13.1 | Research to create buy shares | 5 | 5
|  | T13.2 | Design a solution for buy shares | 6 | 5
|  | T13.3 | Implement the solution | 8 | 8
|  | T13.4 | implement the test cases | 3 | 3
implementing the Broker service - sell | 14 | T14.1 | Research to create sell shares | 3 | 3
|  | T14.2 | Design a solution for shell shares | 2 | 3
|  | T14.3 | Implement the solution | 5 | 5
|  | T14.4 | implement the test cases | 2 | 2
Create player profile interface | 15 | T15.1 | Draw a wireframe | 1 | 1
|  | T15.2 | implement the GUI | 10 | 10
Create side bar access in GUI | 16 | T16.1 | Draw a wireframe | 1 | 1
|  | T16.2 | Implement the GUI for the side bar | 10 | 9
|  |  | Sprint Countdown: | 67 | 67 | 0 | 0 | 0 | 0 | 0

## Sprint 3 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections

## Sprint 4
Sprint Goal: | Aiming for a A grade
Sprint Goal: | Aiming for a A grade
Start Date: | 2016-05-20
End Date: | 2016-05-26
User Story | PBL ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Sprint Countdown: | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections