## Product Backlog
ID | Theme | As a/an | I want to… | so that… | Notes | Priority | Sprint # | Status
| Simulator |  | implementing the simulator Architecture |  |  |  | 1 | Done
| Simulator |  | implementing the simulator Frontend Architecture |  |  |  | 1 | Done
| Simulator | Market | Creating Stock Market (Pre defining data) |  |  |  | 1 | TODO
| Game | Player | show stock data (Pre defined data) |  |  |  | 1 | Done
| Game | Player | Player can buy shares |  |  |  | 1 | Done
| Simulator | Player | Play a game made up of fixed-duration turns | I have only a limited time to decide what to buy and sell | This is an essential property of the game. |  |  | TODO
| Simulator | Player | Know how many turns have passed since the start of the game | I know how far into the game I am |  |  |  | TODO
| Simulator | Player | Have a fixed number of turns in a game | The game has a fixed duration. | We don’t want the game to go on forever… |  |  | TODO
| Simulator | Player | See variation between the prices of shares in the market. | Share prices do not always change at the same rate/have the same price. | This is the stock value model |  | 1 | TODO
| Game | Player | be able to buy shares | they can make money | This needs refinement |  | 1 | TODO
| Game | Player | be able to see the current price of shares | they can decide what to buy/sell |  |  | 1
| Bank | player | I have to create a bank account | to buy shares need money |  |  |  | TODO
| Bank | player | be able to do transaction | to deposit & withdraw money in each turn, also to check balance |  |  |  | TODO
| Player | Broker | Create stock account | Can consist portfolio & transaction history |  |  | 1 | Done

## Sprint 1
Sprint Goal: | Aiming for a D grade
Start Date: | 2016-05-20
End Date: | 2016-05-26
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
implementing the simulator Architecture | 1 | T1.1 | Reasearch to stock exchange simulator to create architecture | 10 | 10
|  | T1.2 | Design a solution for stock simulator architecture | 5 | 5
|  | T1.3 | Impkement the solution | 2 | 2
implementing the simulator frontend Architecture | 2 | T2.1 | Research to create frontend architecture | 5 | 5
|  | T2.2 | Design a solutio for stock simulator architecture | 2 | 2
|  | T2.3 | Implement the solution | 3 | 3
As a Player, I want to create an bank account | 3 | T3.1 | Reasearch to create bank account | 5 | 5
|  | T3.2 | Design a solution for create bank account | 8 | 6
|  | T3.3 | Create Test Cases | 5 | 5
|  | T3.4 | Implement the solution | 12 | 12
As a Player, I want to see variation between the prices of shares in the market.so that share prices do not change at the same rate/have the same price. | 4 | T4.1 | Read the Project Spec | 2 | 2
|  | T4.2 | Design the stock market simulator | 6 | 0
|  | T4.3 | Create Test Cases | 3 | 0
|  | T4.4 | Implement the design | 7 | 0
As a Player, I want to be able to buy shares so that I can make money | 5 | T5.1 | Storyboard a UI to capture BUY commands | 3 | 0
|  | T5.2 | Design a Service to handle the incoming request |  | 0
|  | T5.3 | Create Test Cases |  | 0
|  | T5.3 | Implement the Service |  | 0
|  | T5.5 | Implement the UI |  | 0
|  | T5.6 | Connect the Service to the UI |  | 0
As a Player, I want to be able to see the current price of shares so that they can decide what to buy/sell | 6 | T6.1 | Storyboard a UI to show this information |  | 0
|  | T6.2 | Design a Service to expose this information |  | 0
|  | T6.3 | Create Test Cases |  | 0
|  | T6.4 | Implement the Service |  | 0
|  | T6.5 | Implement the UI |  | 0
|  | T6.6 | Connect the Service to the UI |  | 0
0
0
0
|  |  | Sprint Countdown: | 78 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 1 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections

## Sprint 2
Sprint Goal: | Aiming for a C grade
User Story | PBL ID# | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Sprint Countdown: | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 2 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections

## Sprint 3
Sprint Goal: | Aiming for a B grade
User Story | PBL ID# | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Sprint Countdown: | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 3 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections

## Sprint 4
Sprint Goal: | Aiming for a A grade
User Story | PBL ID# | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Sprint Countdown: | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 -Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
General Reflections